## Priority - Draft - All
Priority | Item | Safety | Energy / Conservation | Maintenance | Upgrade | Easy / Not too expensive (or estimated cost) | Sponsorship Interest | Target / Progress Update
A | Replace amber plastic window in balcony of Sanctuary with clear glass |  | x |  | x |  | X | 2009 | done
A | Replace flat roof over Godly Play class rooms / library with new tar and gravel roof |  |  | x |  | 10000 + |  | 2010-2011 | done
A | Add awning above exterior exit door (2nd floor office) |  | x |  |  |  |  | Majority of heat transfer through wall. Insultation likely a better solution.
A | Repair gutters outside Lepo Room |  |  | x |  | x |  | 2010-2011 | done
A | Repair wall-to-deck flashing, interior courtyard above MDS storage room. |  |  | x |  |  |  | transferred to new list 3/2015
A | Evaluate need to install collection box and additional drain lines to Lovell, from interior courtyard 4" drain line. | [6 empty] | Evaluate during 2009 rainy season, along with drain system | done
A | Insert vertical bars (or other child-protection) in exterior handrails leading to Sanctuary. | x |  |  |  | depends on approach |  | transferred to new list 3/2015
A | Prep and touch up paint / exterior walls |  |  | x |  |  |  | worked on this during May 2008 workday, completed repair at Hammond Hall ramp | done
A | Clean slate roof, Lovell side of steeple |  |  | x |  |  |  | Fall 2008 workday item | done
A | Electrical inspection, MDS & COS (request by MDS, we also need to know about this prior to any lighting upgrades in Sanctuary) | x | x | x | x |  |  | Possible grounding needed in some outlets (see 3/2015 list) | done
A | New light fixtures, MDS |  | x |  | x |  |  | Resolved with updated bulbs | done
A | Repair roof leak, tar and gravel above Old Mill St. entrance. |  |  | x |  |  |  | Completed 2010-2011 | done
A | Develop BMP for storage of chemicals, volatiles | x | [5 empty] | 2010-2011 | done
? | Develop 'procedures' book for facilities (e.g., irrigation system, circuit box locations, shut off valve locations). | x | x |  |  |  |  | transferred to new list 3/2015
? | Mount power strips on wall of main office and 2nd floor office to facilitate use / accessibility. |  | x | [5 empty] | done
? | Replacement of incandescent light fixtures with CFLs |  | x |  |  |  |  | 2015: Moving forward with LED technology | done
? | Improve insulation in ceiling and walls of Choir Room |  | x |  |  |  |  | Investigated during repairs. Walls are insulated (fiberglass batt). Not sure about ceiling, but cathedral design, so harder to modify. Vinyl frame, dual pane IGU windows installed 2007, courtyard side of Choir Room. Add awning? transferred to new list 3/2015
? | Install tank dam in Leppo restroom toilet (water conservation) |  | x |  |  |  |  | Note: We have received many complaints about this toilet plugging up. Installing tank dam would exacerbate this problem. Consider replacing with more efficient, but better functioning toilet. Problem appears resolved as of 3/2015 | done
? | Install motion sensor for lights in Sacristy. |  | x |  |  |  |  | Not necessary | done
? | Replace thermostat in Sacristy. |  | x |  |  |  |  | Not necessary | done
? | Develop plan (and priorities) to replace existing single pane windows with dual pane IGUs. Consider low-E films. Evaluate appropriate frame type (s). |  | x |  |  |  |  | Completed 2013 | done
? | Install vent hood on stove in kitchen. | x | [5 empty] | transferred to new list 3/2015
? | Install paper towel holder in restroom, Sunday School rooms | x | [6 empty] | done
? | Add tank dam to toilet, Sunday School rooms |  | x |  |  |  |  | Any problems with this toilet? - No problems found as of 3/2015 | done
? | Redesign / renovate exiting from back deck; arrangement and access of garbage & recycling containers | x | [5 empty] | transferred to new list 3/2015
? | Selective removal of exiting vegetation, incorporate native / drought tolerant (or other criteria). |  | x |  | x |  |  | transferred to new list 3/2015
B | Improve choir room--create storage, install hardwood floor over existing vinyl (pull up existing vinyl?). Extend hardwood floor into hallway? |  |  |  | x |  |  | transferred to new list 3/2015
B | Re-key COS and MDS doors. Use already developed 'A-E' hierarchy system, or other. |  |  |  | x | 15,000+ |  | transferred to new list 3/2015
B | Inspect ceiling area in Lepo Room and hallway, check for moisture damage. |  |  | x |  | x |  | With new roof in 2010-2011 | done
B | Evaluate needed upgrades for organ, bid and conduct repairs. |  |  | x |  |  |  | Completed ~2010 | done
B | Obtain piano for sanctuary |  |  |  | x |  |  |  | done
B | Repair roof edge above Lepo Room as needed |  |  | x |  | x |  | 2008 | done
B | Install window on Lovell Ave. side of Rector's office (more light into the office). |  |  |  | x |  |  | transferred to new list 3/2015
B | Install fan system to obtain negative pressure in the Catacomb This would require closing off vents on 'neighbor' side of COS & installing minimum 6-mil plastic ground cover. | x |  | x |  | 4000 |  | dropped from list as of 3/2015. May review when drought ends.
B | Frame-in and install new door in Rector's office (separate office from portion of current office with alarm box). Remove existing rear entrance? |  |  |  | x |  |  | Looking at accordian door instead of swinging door option. Deemed unnecessary in 3/2015
B | Install motion sensor on light at outside entrance to Fireside Room | x |  | x |  |  |  | transferred to new list 3/2015
B | Inspect. If necessary install insulation in exterior wall of upstairs office (Gay and Este’s office) |  | x |  |  |  |  | Inspected during 2008.
B | Replace existing windows in upstairs office with dual-pane, energy efficient windows |  | x |  |  |  |  | 2013 | done
B | Replace windows in Godly Play classrooms with dual-pane, energy efficient windows |  | x | x |  |  |  | 2013 | done
B | A light to illuminate the outside bulletin board at the entrance to the Fireside Room (could be a light fastened to the top of the bulletin board, shining downward) |  |  |  | x |  |  | Inspected during 2008. transferred to new list 3/2015
B | Install a handrail in the middle of the stairs to the sanctuary. Could be removable. | x |  | x | x |  |  | transferred to new list 3/2015
B | Put up shelves in middle closet, Fireside Room |  |  | x | x |  |  | Dropped in 3/2015 | x
B | Upgrade steps to stage, Choir Room | x |  |  | x |  |  | transferred to new list 3/2015
C | New lights in the Sanctuary |  |  |  | x | $30,000 - $80,000 |  | transferred to new list 3/2015
C | Hook convective heating system into thermostat controller |  | x |  |  |  |  | Dropped. On timer switch for direct control.
C | Complete removal of asbestos pipe insulation in drop ceiling of MDS area. Install new insulation | x |  |  |  | 13000 |  | Dropped in 3/2015
C | Repair wood damage in back corner storage room |  |  | x |  |  |  | transferred to new list 3/2015
C | Install solar panel(s) on roof [options include Godly Play roof, Choir Room roof] |  | x |  |  |  |  | 2010-2011 | done
C | Renovate ‘small kid room’ at back of Sanctuary |  |  |  | x |  |  | 2015 | done
C | A light to illuminate ‘Our Saviour’ sign located at corner of Lovell and Old Mill (probably a light on the ground shining upward) |  |  |  | x |  |  | transferred to new list 3/2015
C | Acoustical ceiling tile in Fireside Room (or other fix to make room surfaces more acoustically absorbent) |  |  | x | x |  |  | transferred to new list 3/2015
C | Install timers on Fireside Room electric heating registers |  |  |  | x
C | Replace back deck. May need to replace stairs prior to entire deck. | x |  |  | x |  |  | no immediate urgency for deck.
D | Repair / clean out downspout, adjacent to Library entrance. |  |  | x |  |  |  | done, but this is an annual task
D | Prune, pull, vegetation in our side lot. Remove plants climbing on walls (climbing ivy?) |  |  | x |  |  |  | Done, May 2008 workday. Still a maintenance item
D | Replace existing windows in Choir Room with dual-pane, energy efficient windows. |  | x |  |  |  | X | done
D | Install fan motor to make the convective heat distribution system at the rear of the Sanctuary functional again. |  | x | x |  | x |  | done
D | Install light in small stall of ladies' room | x |  | x |  | x |  | done
D | Install new faucet in Hammond Hall kitchen |  |  |  | x | x |  | done
D | Clean carpets in office space |  |  | x |  | x |  | done
B | Install dishwasher in Fireside Room |  |  |  | x |  |  | done
B | Install 'circulation' pump on the hot water system. Alternatively, install on-demand hot water system at Fireside Room sink. |  | x | x | x |  |  | done
D | Enclose wires for track lighting, Choir Room, in that conduit material | x | [5 empty] | done
D | Tie in drainage from Catacomb area to gravity drain to Throckmorton |  |  | x |  |  |  | done
D | Purchase new, light-weight tables for Hammond Hall and general COS use |  |  |  | x |  | X | done
D | Planter boxes |  |  | x |  |  |  | done
A | Make toilet in restroom next to library functional |  |  | x |  | x |  | done
D | Remove excess dirt from crawlspace area in back of chair storage room. |  |  | x |  |  |  | done, as part of drainage work
A | Redirect down spouts from flat roof at entrance to Fireside Room. Bypass planter boxes. |  |  | x |  |  |  | done
A | New sound system in the Sanctuary |  |  |  | x |  |  | done
Note on I67: Reviewer: We opted for the circulation pump.